## Requested
Scheme | Location | Quote Provided | Payment Received | Drawing Reviewed | Drawing Approved | Config Reviewed | Config Approved | Date Approved | Comments
Barton Hill Drive S278 | Outside Number 302 Barton Hill Drive | Yes - 21/05/2025 | Yes | Yes | No | No | No |  | Not accepted due to proximity to accesses. Recommended a zebra and road speed reduction
Pembury Road Care Home Owlsnest | Tonbridge Road / Private Hospital Access | Yes - 11/07/2025 | Yes | Yes | No | Yes | No |  | Not accepted due to long crossing, amongst other things
Navigators Walk S38 | Nash Road near Manston Road | Yes - 22/08/2025 | No | [5 empty] | Not yet had acceptance of quote
Folkestone A Brighter Future | Central Station Crossing (zebra upgrade) | No - Internal scheme | N/A | Yes | Yes | Yes | yes | 2025-10-07 | Departures sent for layout. Discussion about config with Swarco
Folkestone A Brighter Future | Middelburg Square / Cheriton Gardens | No - Internal scheme | N/A | Yes | Yes | Yes | Not yet | 2025-10-07 | Departures sent for layout. Discussion about config with Swarco
Folkestone A Brighter Future | Middelburg Square / Shellons Street | No - Internal scheme | N/A | Yes | Yes | Yes | Not yet | 2025-10-07 | Departures sent for layout. Discussion about config with Swarco
Folkestone A Brighter Future | Middelburg Square Crossing | No - Internal scheme | N/A | Yes | Yes | Yes | yes | 2025-10-07 | Departures sent for layout. Discussion about config with Swarco
Folkestone A Brighter Future | Radnor Park Crossing | No - Internal scheme | N/A | Yes | No | Yes | No |  | Not accepted due to proximity to accesses. Recommended a zebra
Folkestone A Brighter Future | Shellons Street Crossing | No - Internal scheme | N/A | Yes | Yes | Yes | yes | 2025-10-07 | Departures sent for layout. Discussion about config with Swarco
Lower Thames Crossing | East of Marling Cross North Rbt (2-phase toucan crossing S088) | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Pegasus Crossing S087 | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Pegasus Crossing S081 | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Pegasus Crossing S082 | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | East of Henhurst Road Rbt (toucan crossing S090) | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Pegasus Crossing near Scotland Yard (crossing S083) | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Pegasus Crossing near Jeskyns Country Park (crossing S085) | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Marling Cross North Rbt | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Brewers Road / Brewers Road Slip Road | No - time claimed back | N/A | Yes | No | No | No |  | Linked to S087. Layout concerns emailed to David Pye. No config seen yet
Lower Thames Crossing | Marling Cross South Rbt | No - time claimed back | N/A | Yes | No | No | No |  | Layout concerns emailed to David Pye. No config seen yet
Howe Barracks | 06/0813 St Martins Hill near Querns Road | Yes - years ago | Yes | yes | Yes | Abandoned | Abandoned |  | Drawings completed. Requires configuration and linsig review. Crossing requires upgrade due to link to junction below, however this was not part of S278 and was abandoned
Howe Barracks | Littlebourne Road / Spine Road | Yes - years ago | Yes | yes | Yes | yes | yes |  | Drawings completed. Requires configuration and linsig review
SW003534 | Millen Road, Sittingbourne | Yes - 04/09/2025 |  | Yes |  |  |  |  | Outline reviewed, more info required. Emailed to get in touch
SW003535 | Mill Way, Sittingbourne | Yes - 04/09/2025 |  | Yes |  |  |  |  | Outline reviewed, more info required. Emailed to get in touch
Faversham Cross Town Improvements | A2 London Road near Canute Road | Not yet | [6 empty] | Reviewed the initial location, asked for a drawing with the signal equipment shown
Fastrack Improvement Schemes | A206 Crossways Boulevard | No - Internal scheme | N/A | Yes |  |  |  |  | Outline reviewed, more info required but have asked for comments
Fastrack Improvement Schemes | A225 Princes Road | No - Internal scheme | N/A | Yes |  |  |  |  | Outline reviewed, more info required but have asked for comments
Fastrack Improvement Schemes | Marsh Street North | No - Internal scheme | N/A | Yes |  |  |  |  | Outline reviewed, more info required but have asked for comments
A28 Chilmington Development | Chilmington Green Road Toucan near Chilmington Avenue | Yes - 03/09/2025 | Journal code payment being sent soon | Yes | No | Yes | No |  | Journal code payment to be made, but comments have been sent back. With Jamie Hare to consider speed limit change
Wincheap Relief Road | Simmonds Road / Wincheap A28 | Yes - 09/09/2025 | yes | yes | no | yes | no |  | Sent comments 16/10/2025
Wincheap Relief Road | Cow Lane / Wincheap A28 | Yes - 09/09/2025 | yes | yes | no | yes | no |  | Sent comments 16/10/2025
Wincheap Relief Road | Cow Lane / Simmonds Road | Yes - 09/09/2025 | yes | yes | no | yes | no |  | Sent comments 16/10/2025
Wincheap Relief Road | A28 Wincheap near York Road | Yes - 09/09/2025 | yes | yes | no | yes | no |  | Sent comments 16/10/2025
Shottendane Road Roundabout S278 | Shottendane Road Toucan | Yes - 08/09/2025 | [6 empty] | Sent quote for TA
Shottendane Road Roundabout S278 | Southern Access Toucan | Yes - 08/09/2025 | [6 empty] | Sent quote for TA
SW003538 S278 Pond Farm, A2 Newington | Pond Farm Puffin | Yes - 24/10/2025

## Progressing
Scheme | Location | Quote Provided | Supplier | Payment Received | Added to IMTRAC | FAT Scheduled | FAT Complete | SAT Scheduled | Comments
Folkestone A Brighter Future | Central Station Crossing (zebra upgrade) | Yes - 08/10/2025 | Swarco | No | Yes
Folkestone A Brighter Future | Middelburg Square / Cheriton Gardens | Yes - 08/10/2025 | Swarco | No | Yes
Folkestone A Brighter Future | Middelburg Square / Shellons Street | Yes - 08/10/2025 | Swarco | No | Yes
Folkestone A Brighter Future | Middelburg Square Crossing | Yes - 08/10/2025 | Swarco | No | Yes
Folkestone A Brighter Future | Shellons Street Crossing | Yes - 08/10/2025 | Swarco | No | Yes
Howe Barracks | Littlebourne Road / Spine Road | Yes - 07/10/2025 | Yunex | Yes | Yes
A28 Chilmington Development | Chilmington Green Road Toucan near Chilmington Avenue | Not yet, but built on street | Yunex | Journal code payment being sent soon | No |  |  |  | Journal code payment to be made, but comments have been sent back. With Jamie Hare to consider speed limit change. Built on street but not agreed